## Project Tasks
ID | Sprint | Task | Status | Owner | Date | Notes
001 | Setup | Project structure | Done | Abhay | 2026-08-22 | Initial repository structure created
002 | Setup | Conda environment | Done | Abhay | 2026-08-22 | IPL_Intelligence_Platform / Python 3.12.13
003 | Data | Cricsheet dataset profiling | Done | Abhay | 2026-08-22 | Profiled raw JSON dataset
004 | Database | PostgreSQL verification | Done | Abhay | 2026-08-22 | PostgreSQL 17.6 service verified
005 | Database | Python database connection | Done | Abhay | 2026-08-22 | SQLAlchemy connection test successful
006 | Database | Database schema design | Done | Abhay | 2026-09-03 | Finalized PostgreSQL dim/fact model plus ETL audit and DQ issue tables.
007 | ETL | JSON ingestion pipeline | Done | Abhay | 2026-09-03 | End-to-end JSON ingestion completed; 1,243/1,243 files successful.
008 | ETL | Validation and data-quality checks | Done | Abhay | 2026-09-03 | Structural validation + DQ framework implemented; 60 warnings, 0 blocking errors in full run.
009 | Analytics | Player/team/venue analytics | Done | Abhay | 2026-09-22 | Player batting/bowling, team batting/bowling, match summary/innings, and venue analytics implemented and verified against PostgreSQL.
010 | ML | Win prediction feature engineering | Pending
011 | ML | Model training and evaluation | Pending
012 | GenAI | GenAI assistant | Pending
013 | RAG | RAG knowledge pipeline | Pending
014 | API | Backend API | Pending
015 | Frontend | User interface | Pending
016 | Deployment | Production deployment | Pending
17 | ETL | Inspect Cricsheet source schema | Done | Abhay | 2026-08-26
18 | ETL | Build JSON reader | Done |  | 2026-08-26
19 | ETL | Build match parser | Done |  | 2026-08-26
20 | Validation | Build match validator | Done | Abhay | 2026-09-03 | Structural match validator implemented and negative cases verified.
21 | ETL | Build transformation layer | Done | Abhay | 2026-09-03 | Validated domain records transformed into database-ready package.
22 | ETL | Build PostgreSQL loader | Done | Abhay | 2026-09-03 | Loaded dimensions, match relationships, innings, deliveries, extras and wickets.
23 | ETL | Implement ETL audit logging | Done | Abhay | 2026-09-03 | ETL run and file-level audit status/stage/duration/error tracking implemented.
24 | ETL | Full IPL ingestion run | Done | Abhay | 2026-09-03 | Run 7: 1,243 discovered, 1,243 processed, 1,243 successful, 0 failed.
25 | ETL | Verify loader idempotency | Done | Abhay | 2026-09-03 | Reran match 1082591; business-row counts unchanged.
26 | ETL | Source integrity verification | Done | Abhay | 2026-09-03 | 1,243 JSON files; numeric/unique match IDs; no duplicate IDs.
27 | ETL | Source-to-database reconciliation | Done | Abhay | 2026-09-03 | Matches, innings, deliveries, extras and wickets all reconciled exactly.
28 | Validation | Data-quality rule framework | Done | Abhay | 2026-09-03 | Severity-based DQ result model with ERROR/WARNING handling implemented.
29 | Validation | Persist data-quality issues | Done | Abhay | 2026-09-03 | Persisted file-level DQ issues into etl_file_quality_issue and verified audit relationship.
30 | Validation | Full DQ warning analysis | Done | Abhay | 2026-09-03 | Full dataset: DQ010=51 warnings, DQ011=9 warnings, total=60, errors=0.
31 | Testing | Full regression test suite | Done | Abhay | 2026-09-03 | 23 tests passed after DQ integration.
32 | Documentation | Update engineering documentation | Done | Abhay | 2026-09-03 | Updated architecture, data dictionary, database, ETL, testing, troubleshooting, DQ and change log docs.
33 | Project Management | Professional Git workflow | Done | Abhay | 2026-09-03 | Added branch/commit/PR workflow guidance for solo development simulation.
34 | Analytics | Implement match analytics | Done | Abhay | 2026-09-10 | Match summary and innings analytics implemented; verified across multiple real matches.
35 | Analytics | Implement venue analytics | Done | Abhay | 2026-09-22 | Venue statistics and top-venues analytics implemented; 9 venue tests and real PostgreSQL validation passed.

## Issues
Issue ID | Problem | Cause | Solution | Status
BUG-001 | Conda not recognized in PowerShell | Shell integration / execution policy | Configure PowerShell for Conda and verify activation | Resolved
BUG-002 | No module named 'src' | Script executed directly from scripts directory context | Run as module: python -m scripts.test_database_connection | Resolved
BUG-003 | pip path appeared to use user-level Python | User-level pip was visible during initial diagnostic | Verified environment pip/package import paths using conda list, where.exe, sys.path and pip.__file__ | Resolved
BUG-004 | Simple over_number + ball_number uniqueness falsely flagged valid illegal deliveries | Source delivery numbering is not a safe uniqueness key around wides/no-balls | Use delivery_sequence and enforce uniqueness on innings_id + over_number + delivery_sequence | Resolved

## Architecture Decisions
Date | Decision | Reason | Status
2026-08-22 | Use PostgreSQL | Reliable relational database for detailed cricket event data and analytics | Accepted
2026-08-22 | Use SQLAlchemy | Centralize database connectivity and support maintainable Python database code | Accepted
2026-08-22 | Preserve raw JSON | Maintain reproducibility and data lineage | Accepted
2026-08-22 | Use delivery-level fact data | Preserve detailed event-level information for analytics and ML feature generation | Accepted
2026-08-22 | Separate structured data from RAG knowledge | Avoid using vector search where relational/analytical queries are more appropriate | Accepted
2026-08-26 | Normalize historical team aliases | Prevent renamed IPL franchises from becoming separate analytical teams | Accepted
2026-08-26 | Use delivery_sequence for delivery-position uniqueness | Avoid false duplicate detection caused by illegal deliveries and source ball numbering | Accepted
2026-09-03 | Separate DQ issues into an audit table | Keep data-quality observations queryable without mixing them into cricket fact tables | Accepted
2026-09-03 | Treat DQ warnings as non-blocking | Incomplete but usable records can load while remaining visible for audit | Accepted
2026-09-03 | Treat DQ errors as blocking | Prevent structurally/logically invalid records from reaching analytical tables | Accepted
2026-09-03 | Require source-to-DB reconciliation before downstream analytics | Establish a measurable data-integrity gate before ML/analytics | Accepted
2026-09-03 | Use logical Git commits and PRs | Simulate professional team development workflow and maintain reviewable history | Accepted
2026-09-22 | Do not silently canonicalize venue-name variants in analytics | Venue aliases can represent the same physical venue; merging them inside analytics without an explicit master-data rule could change historical aggregates and make the transformation non-auditable. | Accepted